## Sheet1
Task Number | Task Name | Intake, Design, Setup, Operations | Major Milestone | Critical Path? | Dependency Task Number | Dependency Task Name | Duration | Start | Finish | Status | % Completion | Score | Client Owner | ANSR Owner | Task Owner | Toggle for Client | Comments
1.1.1 | EB questionnaire completion by client | Intake |  |  |  |  | 7 | 2024-09-19 | 2024-09-30
1.1.3 | Client brand assets (guideline, logo files, image repository) | Intake |  |  |  |  | 7 | 2024-09-19 | 2024-09-30
1.1.5 | EB workshop 2: ANSR to understand client: Company vision, brand goals, persoSelf, talent persoSelflity​ | Intake |  |  |  |  | 4 | 2024-10-02 | 2024-10-08
1.1.6 | EB workshop 3: ANSR to conduct focus group discussion with client on EB questionnaire | Intake |  |  |  |  | 4 | 2024-10-09 | 2024-10-15
1.2.1 | Intake meeting with Client on requirement | Intake |  |  |  |  | 4 | 2024-09-23 | 2024-09-27
1.9.3 | Create mailer series: Short mail, hub content | Design |  |  |  |  | 1 | 2024-10-15 | 2024-10-16
1.9.2 | Seek alignment on key asks from Client | Design |  |  |  |  | 1 | 2024-10-11 | 2024-10-14
1.9.1 | Workshop with Client to present CCE Concept | Design |  |  |  |  | 3 | 2024-10-07 | 2024-10-10
1.8.7 | Publish to recruiting team and PCP team to add in HII workshop | Design |  |  |  |  | 1 | 2024-11-12 | 2024-11-13
1.8.6 | Receive client approval for the Hiring Manager Talking Points collateral | Design |  |  |  |  | 5 | 2024-11-04 | 2024-11-11
1.8.5 | Client to conduct legal review | Design |  |  |  |  | 4 | 2024-10-28 | 2024-11-01
1.8.4 | Client to conduct brand review | Design |  |  |  |  | 4 | 2024-10-28 | 2024-11-01
1.8.2 | Client to review and provide feedback on Hiring Manager Talking Points | Design |  |  |  |  | 4 | 2024-10-15 | 2024-10-21
1.7.7 | Publish to recruiting team and PCP team to add in HII workshop | Design |  |  |  |  | 1 | 2024-11-12 | 2024-11-13
1.9.4 | Build calendar of mailer dissemination | Design |  |  |  |  | 1 | 2024-10-15 | 2024-10-16
1.7.6 | Receive client approval for the Recruiter Talking Points collateral | Design |  |  |  |  | 5 | 2024-11-04 | 2024-11-11
1.7.5 | Client to conduct legal review | Design |  |  |  |  | 4 | 2024-10-28 | 2024-11-01
1.7.4 | Client to conduct brand review | Design |  |  |  |  | 4 | 2024-10-28 | 2024-11-01
1.7.3 | ANSR to incorporate client feedbacks | Design |  |  |  |  | 3 | 2024-10-22 | 2024-10-25
1.7.2 | Client to review and provide feedback on Recruiter Talking Points | Design |  |  |  |  | 4 | 2024-10-15 | 2024-10-21
1.7.1 | ANSR to design Recruiter Talking Points and share with client | Design |  |  |  |  | 5 | 2024-10-07 | 2024-10-14
1.8.1 | ANSR to design Hiring Manager Talking Points and share with client | Design |  |  |  |  | 5 | 2024-10-07 | 2024-10-14
1.9.5 | ANSR to present end-to-end program with mailers to Client | Design |  |  |  |  | 2 | 2024-10-17 | 2024-10-21
1.9.8 | ANSR to receive client approval | Design |  |  |  |  | 2 | 2024-10-30 | 2024-11-01
1.9.7 | ANSR to make updates based on client feedback | Design |  |  |  |  | 2 | 2024-10-25 | 2024-10-29
1.10.9 | Share output updates with client | Design |  |  |  |  | 2 | 2024-12-03 | 2024-12-05
1.10.8 | Publish to PCP and TA as FYI | Design |  |  |  |  | 2 | 2024-11-28 | 2024-12-02
1.10.7 | Execute the campaign | Design |  |  |  |  | 5 | 2024-11-20 | 2024-11-27
1.10.6 | Conduct Corporate review | Design |  |  |  |  | 4 | 2024-11-13 | 2024-11-19
1.10.5 | Conduct client legal review | Design |  |  |  |  | 4 | 2024-11-13 | 2024-11-19
1.10.4 | ANSR to align with Client and receive approval | Design |  |  |  |  | 5 | 2024-11-05 | 2024-11-12
1.10.3 | ANSR to recommend market sprint campaign strategy to Client | Design |  |  |  |  | 8 | 2024-10-23 | 2024-11-04
1.10.2 | Identify key external opportunities for brand visibility | Design |  |  |  |  | 5 | 2024-10-15 | 2024-10-22
1.10.1 | Define key objectives of a MSC | Design |  |  |  |  | 5 | 2024-10-07 | 2024-10-14
1.9.15 | Schedule and publish CCE program | Design |  |  |  |  | 2 | 2024-12-03 | 2024-12-05
1.9.14 | Receive approval from client | Design |  |  |  |  | 3 | 2024-11-27 | 2024-12-02
1.9.13 | Confirm integration successful | Design |  |  |  |  | 2 | 2024-11-22 | 2024-11-26
1.9.12 | Dry run of mailers | Design |  |  |  |  | 2 | 2024-11-19 | 2024-11-21
1.9.11 | Configure push notification and mailers on Loop platform | Design |  |  |  |  | 3 | 2024-11-13 | 2024-11-18
1.9.10 | Client to run infosec with ANSR tech team | Design |  |  |  |  | 3 | 2024-11-07 | 2024-11-12
1.9.9 | Share technical requirements with client for CCE setup - Email ID creation, Infosec Protocol, Integration with Client IT Team | Design |  |  |  |  | 2 | 2024-11-04 | 2024-11-06
1.6.7 | Publish to recruiting team and PCP team to add in HII workshop | Design |  |  |  |  | 1 | 2024-11-12 | 2024-11-13
1.9.6 | Receive client feedback on the CCE design | Design |  |  |  |  | 2 | 2024-10-22 | 2024-10-24
1.6.6 | Receive client approval for the Candidate FAQs collateral | Design |  |  |  |  | 5 | 2024-11-04 | 2024-11-11
1.8.3 | ANSR to incorporate client feedbacks | Design |  |  |  |  | 3 | 2024-10-22 | 2024-10-25
1.6.4 | Client to conduct brand review | Design |  |  |  |  | 4 | 2024-10-28 | 2024-11-01
1.3.4 | Client to conduct brand review | Design |  |  |  |  | 4 | 2024-10-28 | 2024-11-01
1.3.3 | ANSR to incorporate client feedbacks | Design |  |  |  |  | 3 | 2024-10-22 | 2024-10-25
1.3.2 | Client to review and provide feedback on Why Join Us collateral | Design |  |  |  |  | 4 | 2024-10-15 | 2024-10-21
1.3.1 | ANSR to design Why Join Us collateral and share with client | Design |  |  |  |  | 5 | 2024-10-07 | 2024-10-14
1.2.11 | Execute Go live | Design |  |  |  |  | 1 | 2024-11-18 | 2024-11-19
1.2.10 | Page readiness D - 2 | Design |  |  |  |  | 1 | 2024-11-14 | 2024-11-15
1.2.9 | Share page with ANSR product team for jobs integration | Design |  |  |  |  | 1 | 2024-11-12 | 2024-11-13
1.2.8 | Receive approval to publish | Design |  |  |  |  | 2 | 2024-11-07 | 2024-11-11
1.2.7 | Send non-live link to client to preview | Design |  |  |  |  | 2 | 2024-11-04 | 2024-11-06
1.2.6 | Receive client approval for the landing page | Design |  |  |  |  | 3 | 2024-10-29 | 2024-11-01
1.6.5 | Client to conduct legal review | Design |  |  |  |  | 4 | 2024-10-28 | 2024-11-01
1.2.4 | Receive feedback from client and incorporate changes | Design |  |  |  |  | 3 | 2024-10-17 | 2024-10-22
1.2.3 | Share mock-up of landing page with client | Design |  |  |  |  | 3 | 2024-10-11 | 2024-10-16
1.2.2 | Creation of content | Design |  |  |  |  | 8 | 2024-09-30 | 2024-10-10
1.1.7 | EB workshop 4: ANSR to provide Overview of CCE to client | Design |  |  |  |  | 4 | 2024-10-16 | 2024-10-22
1.1.4 | EB workshop 1: ANSR provides overview of EB deliverables to client | Design |  |  |  |  | 4 | 2024-09-25 | 2024-10-01
1.1.2 | Define WIIFM "What's in it for me" - EVP statement, cluture, Technology stack, Testimonials, Differentiators, etc. | Design |  |  |  |  | 3 | 2024-10-01 | 2024-10-04
1.3.5 | Client to conduct legal review | Design |  |  |  |  | 4 | 2024-10-28 | 2024-11-01
1.3.6 | Receive client approval for the Why Join Us collateral | Design |  |  |  |  | 5 | 2024-11-04 | 2024-11-11
1.2.5 | Conduct client legal review | Design |  |  |  |  | 3 | 2024-10-23 | 2024-10-28
1.4.1 | ANSR to design Fact Sheet and share with client | Design |  |  |  |  | 5 | 2024-10-07 | 2024-10-14
1.3.7 | Publish to recruiting team and PCP team to add in HII workshop | Design |  |  |  |  | 1 | 2024-11-12 | 2024-11-13
1.6.3 | ANSR to incorporate client feedbacks | Design |  |  |  |  | 3 | 2024-10-22 | 2024-10-25
1.6.2 | Client to review and provide feedback on Candidate FAQs collateral | Design |  |  |  |  | 4 | 2024-10-15 | 2024-10-21
1.6.1 | ANSR to design Candidate FAQs and share with client | Design |  |  |  |  | 5 | 2024-10-07 | 2024-10-14
1.5.6 | Receive client approval for the Benefits Summary collateral | Design |  |  |  |  | 5 | 2024-11-04 | 2024-11-11
1.5.5 | Client to conduct legal review | Design |  |  |  |  | 4 | 2024-10-28 | 2024-11-01
1.5.4 | Client to conduct brand review | Design |  |  |  |  | 4 | 2024-10-28 | 2024-11-01
1.5.3 | ANSR to incorporate client feedbacks | Design |  |  |  |  | 3 | 2024-10-22 | 2024-10-25
1.5.7 | Publish to recruiting team and PCP team to add in HII workshop | Design |  |  |  |  | 1 | 2024-11-12 | 2024-11-13
1.5.1 | ANSR to design Benefits Summary and share with client | Design |  |  |  |  | 5 | 2024-10-07 | 2024-10-14
1.4.7 | Publish to recruiting team and PCP team to add in HII workshop | Design |  |  |  |  | 1 | 2024-11-12 | 2024-11-13
1.4.6 | Receive client approval for the Fact sheet collateral | Design |  |  |  |  | 5 | 2024-11-04 | 2024-11-11
1.4.5 | Client to conduct legal review | Design |  |  |  |  | 4 | 2024-10-28 | 2024-11-01
1.4.4 | Client to conduct brand review | Design |  |  |  |  | 4 | 2024-10-28 | 2024-11-01
1.4.3 | ANSR to incorporate client feedbacks | Design |  |  |  |  | 3 | 2024-10-22 | 2024-10-25
1.5.2 | Client to review and provide feedback on Benefits Summary collateral | Design |  |  |  |  | 4 | 2024-10-15 | 2024-10-21
1.4.2 | Client to review and provide feedback on Fact sheet collateral | Design |  |  |  |  | 4 | 2024-10-15 | 2024-10-21
1.12.4.7 | ANSR to upload content and go live | Setup |  |  |  |  | 2 | 2024-12-06 | 2024-12-10
1.12.3.5 | Client publishes content on LinkedIn Page | Setup |  |  |  |  | 2 | 2024-11-28 | 2024-12-02
1.12.3.6 | Publish to CP/POC/TA and any other teams | Setup |  |  |  |  | 1 | 2024-12-03 | 2024-12-04
1.12.4 | If decision to create affiliate page | Setup |  |  |  |  | 36 | 2024-10-28 | 2024-12-16
1.12.4.1 | ANSR to create recommendation deck for client based on alignment | Setup |  |  |  |  | 8 | 2024-10-28 | 2024-11-07
1.12.4.5 | Client to conduct client legal review | Setup |  |  |  |  | 1 | 2024-11-27 | 2024-11-28
1.12.4.3 | ANSR to receive approval from client | Setup |  |  |  |  | 4 | 2024-11-13 | 2024-11-19
1.12.4.4 | ANSR to build page, social posts and content calendar | Setup |  |  |  |  | 4 | 2024-11-20 | 2024-11-26
1.12.4.6 | ANSR to build page layout and share with client for approval | Setup |  |  |  |  | 4 | 2024-11-29 | 2024-12-05
1.12.3.4 | ANSR to share with client for approval | Setup |  |  |  |  | 4 | 2024-11-21 | 2024-11-27
1.12.4.2 | ANSR to present the recommendation and discuss on outcome | Setup |  |  |  |  | 2 | 2024-11-08 | 2024-11-12
1.12.3.3 | ANSR to work on content planning based on client feedback | Setup |  |  |  |  | 4 | 2024-11-14 | 2024-11-20
1.11.5 | Creat mockups and with client and share with client for approval | Setup |  |  |  |  | 1 | 2024-10-29 | 2024-10-30
1.12.3.1 | ANSR to create section blueprint | Setup |  |  |  |  | 8 | 2024-10-28 | 2024-11-07
1.12.3 | If decision to use parent brand page as 'life' | Setup |  |  |  |  | 28 | 2024-10-28 | 2024-12-04
1.12.2 | Client to provide guidance as to which LinkedIn pages to link for the job postings | Setup |  |  |  |  | 3 | 2024-10-22 | 2024-10-25
1.12.1 | Client to decide whether to publish life on Parent brand page or create an Affiliate page | Setup |  |  |  |  | 5 | 2024-10-14 | 2024-10-21
1.11.8 | Create PO and share with vendor along with approval from client (45 days before first day of onboarding) | Setup |  |  |  |  | 6 | 2024-11-07 | 2024-11-15
1.11.7 | Client to approve design mockups | Setup |  |  |  |  | 2 | 2024-11-04 | 2024-11-06
1.11.6 | ANSR to receive feedback from client | Setup |  |  |  |  | 1 | 2024-10-31 | 2024-11-01
1.11.4 | ANSR to make revisions based on client feedback and share updated options with quote | Setup |  |  |  |  | 1 | 2024-10-25 | 2024-10-28
1.11.3 | ANSR to receive client feedback on catalogue and budget | Setup |  |  |  |  | 1 | 2024-10-23 | 2024-10-24
1.11.2 | ANSR to create preliminary budget for swag and share with client | Setup |  |  |  |  | 1 | 2024-10-21 | 2024-10-22
1.11.1 | ANSR to identify and share product catalogue with recommendation to client | Setup |  |  |  |  | 4 | 2024-10-14 | 2024-10-18
1.12.4.8 | Publish to TA for integration with ATS for auto job publishing | Setup |  |  |  |  | 1 | 2024-12-11 | 2024-12-12
1.12.3.2 | ANSR to share the blueprint with client for approval | Setup |  |  |  |  | 3 | 2024-11-08 | 2024-11-13
1.12.4.9 | Publish to CP/POC/TA and any other teams | Setup |  |  |  |  | 1 | 2024-12-13 | 2024-12-16
1.1 | EB Discovery |  | Ready for Sourcing | Yes |  |  | 24 | 2024-09-19 | 2024-10-22
1.2 | Landing Page |  | Ready for Sourcing | Yes |  |  | 42 | 2024-09-23 | 2024-11-19
1.3 | Recruitment Essential: Candidate Facing collaterals - Why Join Us (External) |  | Ready for Sourcing | Yes |  |  | 28 | 2024-10-07 | 2024-11-13
1.4 | Recruitment Essential: Candidate Facing collaterals - Fact Sheet (Internal) |  | Ready for Sourcing | Yes |  |  | 28 | 2024-10-07 | 2024-11-13
1.5 | Recruitment Essential: Candidate Facing collaterals - Benefits Summary (External) |  | Ready for Sourcing | Yes |  |  | 28 | 2024-10-07 | 2024-11-13
1.6 | Recruitment Essential: Recruiter Collaterals - Candidate FAQs (Internal) |  | Ready for Sourcing | Yes |  |  | 28 | 2024-10-07 | 2024-11-13
1.7 | Recruitment Essential: Recruiter Collaterals - Recruiter Talking Points |  | Ready for Sourcing | Yes |  |  | 28 | 2024-10-07 | 2024-11-13
1.8 | Recruitment Essential: Recruiter Collaterals - Hiring Manager Talking Points |  | Ready for Sourcing | Yes |  |  | 28 | 2024-10-07 | 2024-11-13
1.9 | Continuous Candidate Engagement program |  | Ready for Offers |  |  |  | 44 | 2024-10-07 | 2024-12-05
1.1 | Market Sprint Campaign |  | Ready for Offers |  |  |  | 44 | 2024-10-07 | 2024-12-05
1.11 | Swag Kit |  | Ready for Onboarding |  |  |  | 25 | 2024-10-14 | 2024-11-15
1.12 | Online Presence (LinkedIn, Twitter, etc.) |  | Ready for Sourcing |  |  |  | 46 | 2024-10-14 | 2024-12-16